# Phase 1 — Internal MVP: Execution Guide (Corrected)

Scope is strictly these **6 modules** — nothing more:

1. Authentication & Roles (Admin, Manager, Employee, Client)

2. Client Management

3. Project Management

4. Task / Kanban Board

5. Document Management

6. Client Dashboard

1. Before Anyone Writes Code (Day 1, half a day)

Do this together as a team:

1. Create the GitHub repo (private), add all 3 devs, protect `main` (PR + 1 approval required).

2. Agree on branch naming: `feature/<module-name>-<piece>`, e.g. `feature/auth-login`, `feature/client-crud`.

3. Create a shared task board (GitHub Projects is enough) with **6 columns matching the 6 modules** — not "To do / Doing / Done." This keeps everyone's eyes on module scope, not vague task piles.

4. Everyone installs: Python 3.12.7, Docker Desktop, VS Code (+Python, Pylance, Docker extensions).

5. Write one shared `.env.example`.

**Done when:** everyone can `git clone`, run one Docker command, and see a blank page.

---

2. Team Split — Mapped to the 6 Modules

| Person | Owns (backend + frontend, end to end) | Supports |

|---|---|---|

| **Dev 1 — Foundation lead** | Module 1 (Auth & Roles), Module 2 (Client Management) | Reviews role-filtering logic used by everyone else |

| **Dev 2 — Delivery lead** | Module 3 (Project Management), Module 6 (Client Dashboard) | Client Dashboard depends on Project data, so same person keeps context |

| **Dev 3 — Execution lead** | Module 4 (Task/Kanban Board), Module 5 (Document Management) | Runs integration testing across all 6 modules |

Each person owns their modules **fully** — API and UI both — rather than

splitting "backend person" vs "frontend person." In a 3-person team this

avoids hand-off delays; you only have 3 people, don't create a 4th

dependency chain between them.

If you (founder) are one of the three, take **Dev 3's spot** — Task/Kanban

and Documents are the modules every employee touches daily, so you'll feel

real usage friction fastest.

---

#3. Build Order & Weekly Plan

Modules are **sequential where they depend on each other**, parallel where

they don't:

```

Module 1 (Auth & Roles)

│

▼

Module 2 (Client)  ──┐

├──▶ Module 3 (Project) ──▶ Module 6 (Client Dashboard)

Module 4 (Task) ─────┤

Module 5 (Document) ─┘

```

Module 1 blocks everything — nobody can build a role-filtered screen until

roles exist. Modules 2, 4, 5 can start in parallel once Module 1's auth

middleware exists. Module 3 needs Module 2 (a project belongs to a client).

Module 6 needs Module 3 (dashboard shows project progress).

Week 1 — Module 1: Authentication & Roles

*(All 3 devs — this module blocks everyone, so build it together)*

| Day | Task |

|---|---|

| 1 | Docker Compose (Postgres + FastAPI skeleton). Streamlit app skeleton. |

| 2 | Database schema: `organizations`, `users` tables + Alembic migration. |

| 3 | `/auth/register`, `/auth/login` — JWT issue, password hashing (bcrypt). |

| 4 | Role middleware — every endpoint checks role + `organization_id` server-side. |

| 5 | Streamlit login page wired to the API. Test: each of the 4 roles can log in and land on an empty, role-labeled home screen. |

**Checkpoint (Friday demo):** All 4 roles can log in. An Employee hitting an Admin-only endpoint via Postman gets rejected — not just hidden in the UI.

### Week 2 — Modules 2, 4, 5 in parallel

| Dev 1 — Module 2 (Client) | Dev 3 — Module 4 (Task/Kanban) | Dev 3 continues — Module 5 (Document) |

|---|---|---|

| Client CRUD API | Task model + status-update API | *(starts once Module 4 is stable)* |

| Client list/add/edit UI in Streamlit | Kanban board UI (To do/In progress/Testing/Done) | File upload API (local MinIO) + upload UI |

*(Dev 2 uses this week to prep Module 3 — reading the Client API docs, drafting the Project schema, so Week 3 starts immediately.)*

**Checkpoint:** Admin can add a client. A task can be created and moved across the board. A file can be uploaded and listed.

Week 3 — Module 3: Project Management

*(Dev 2 leads; Dev 1 and Dev 3 support since their modules are stable)*

| Day | Task |

|---|---|

| 1-2 | Project CRUD API — linked to `client_id`, includes budget/deadline/status. |

| 2-3 | Team assignment (many-to-many project ↔ users). |

| 3-4 | Project management UI: create project, assign team, see status. |

| 5 | Integration: a Manager logs in and sees only their assigned projects; an Admin sees all. |

**Checkpoint:** A project can be created under a client, a team assigned, and role-based visibility (Admin sees all, Manager sees own) actually works.

Week 4 — Module 6: Client Dashboard + Full QA

| Day | Task |

|---|---|

| 1-2 | Read-only Client API: progress %, milestones, document list — scoped strictly to that client's own project. |

| 3 | Client Dashboard UI: progress ring, milestone list, documents. |

| 4 | Full QA pass — run the checklist in Section 5, all 6 modules together. |

| 5 | Load one real Affordable AI project's real data. Get 2-3 real employees to use it for a day. |

**Checkpoint:** A Client logs in and sees only their own project's progress — nothing else. Real people have used the real system, not a demo.

---

4. Techniques to Use Throughout

- **API-first**: agree on request/response shape before coding each module's endpoints.

- **Alembic migrations only** — never hand-edit the database schema.

- **Small PRs, one module-piece at a time**, reviewed by someone who doesn't own that module.

- **`.env` for all config/secrets** — never hardcoded, never committed.

- **pytest for every endpoint's happy path + its role-rejection path.**

- **Daily 15-minute standup**, organized around the 6 modules: "which module am I on, what's blocking me."

- **Friday demo every week** — show the module(s) completed that week, working, to the whole team.

---

5. Definition of Done — Full Checklist (All 6 Modules)

- [ ] **Module 1**: All 4 roles can log in; wrong-role API access is rejected server-side, tested with Postman/curl, not just hidden in UI

- [ ] **Module 2**: Client CRUD works; only Admin can create/delete clients

- [ ] **Module 3**: Project CRUD works; Manager sees only assigned projects, Admin sees all

- [ ] **Module 4**: Tasks can be created, assigned, and moved across statuses; Employee sees only their own tasks

- [ ] **Module 5**: Documents upload, list, and are scoped to their project — no cross-project leakage

- [ ] **Module 6**: Client sees only their own project's progress, milestones, and documents — verified by logging in as a client account and confirming no other data is reachable

- [ ] The entire app runs with one `docker compose up` on a fresh machine

- [ ] At least 2 real employees have used it for real work

---

## 6. What NOT to Do

- Don't build a "CEO Dashboard" or "PM Dashboard" as a separate module — that's Modules 2/3/4 with role-based filtering, already covered above.

- Don't start Module 3 before Module 2 is stable — a project without a client to belong to is a modeling mistake you'll have to undo.

- Don't add AI anywhere in Phase 1 — not even "just a summary field." That's Phase 2.

- Don't let Streamlit visual polish take time away from getting all 6 modules functionally correct first.

---

## 7. Monday Morning — Where To Literally Start

1. `git init`, push empty repo.

2. `docker-compose.yml` with Postgres + FastAPI "Hello World."

3. Alembic + `organizations` + `users` tables (Module 1 schema).

4. `/auth/register` + `/auth/login`, tested in Postman before any UI exists.

5. Role middleware — reject requests where role doesn't match the endpoint.

6. Only then: wire the Streamlit login page to real login.

That's Week 1, Day 1 through Day 5, in order.